## Slide 1: Class 2DD Group 031 SPRINT 4
Group members:
Diogo Sá Dias (1161605)
Duarte Dias (1190539)

## Slide 2: Sprint planning – Sprint 3
SPRINT BACKLOG | 
Number of stories | 13
Number of bugs | 1
Number of tasks | 52
Number of Management Tasks | 3
Number of team members | Planned: 5 Actual: 5
Total planned estimation vs execution | Planned hours: 102 Executed hours: 90
Planned Start Date: 03Jan2022 Real Start Date: 03Jan2022
Planned Finished Date: 23Jan2022 Real Finish Date: 23Jan2022

## Slide 3: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
US 401 | YES |  |  |  | YES | 
US 402 | YES |  |  |  | YES | 
US 403 | YES |  |  |  | YES | 
US 404 | YES |  |  |  | YES | 
US 405 | YES |  |  |  | YES | 
US 406 | YES |  |  |  | YES | 
US 407 | YES |  |  |  | YES | 
US 409 | YES |  |  |  | YES | 
US 410 | YES |  |  |  | YES | 
US 411 | YES |  |  |  | YES | 
… |  |  |  |  |  | 

## Slide 4: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
… |  |  |  |  |  | 
US 417 | YES |  |  |  | YES | 
US 418 | YES |  |  |  | YES | 
US 420 | YES |  |  |  | YES | 

## Slide 5: Sprint Execution
Issues | Sprint Backlog (a) | Added issues during sprint (b) | Closed issues from initial planning (c) | Closed issues from added ones (d) | Issues not closed (e) | % Execution | 
 |  |  |  |  |  | Planned (c/a) | Total (c+d)/(a+b)
Number of stories (I) | 13 | 0 | 13 | 0 | 0 | 100 | 100
Number of bugs (II) | 3 | 2 | 3 | 2 | 0 | 100 | 100
Number of tasks (III) | 52 | 2 | 52 | 2 | 0 | 100 | 100
TOTAL |  |  |  |  |  |  | 
Total Estimate | 102 h | 4 | 100 | 4 | 0 | 98,8 | 99,1

## Slide 6: Work by team member
Chart: Hours / n. tasks
| Diogo Dias - 1161605 | Duarte Dias - 1190539
Horas / tarefas | 2.5 | 2.5

## Slide 7: Work by type
Chart: Componente
| ESINF | ARQC | BDAD | FSIAP | LAPR3
Componente | 3 | 4 | 4 | 0 | 3

## Slide 8: Sprint 3 - Burndown Chart
Print do JIRA após fecho da sprint
Chart: Sprint 3 - Burndown
| 44564 | 44571 | 44576 | 44582 | 44584
Line | 48 | 42 | 40 | 34 | 3

## Slide 9: Sprint Review
Date: 24Jan2022
Main conclusions:
We should work faster
We should Communicate better.

## Slide 10: Sprint Retrospective
Date: 4Jan2022
What went well?
Better Communication
Great Commitment
What went wrong?
The work could be done earlier
What we’ve learned?
That organized we can work better and Support each others.

## Slide 11: Sprint Retrospective
Date: 24Jan2022
Action items:

## Slide 12: Team performance metrics
Chart: 
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Velocidade | 4 | 2.8 | 2 | 3.2
Controle (máximo desvio padrão) | 2.6 | 4.5 | 2.4 | 3
Burnup | 1 | 0.61 | 0.3 | 1