## Slide 1: Class 2DD Group 031 SPRINT 3
Group members:
Diogo Sá Dias (1161605)
Duarte Dias (1190539)

## Slide 2: Sprint planning – Sprint 3
SPRINT BACKLOG | 
Number of stories | 20
Number of bugs | 5
Number of tasks | 51
Number of Management Tasks | 3
Number of team members | Planned: 6 Actual: 5
Total planned estimation vs execution | Planned hours: 102 Executed hours: 90
Planned Start Date: 06Dec2021 Real Start Date: 06Dec2021
Planned Finished Date: 22Dec2021 Real Finish Date: 03Jan2022

## Slide 3: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
US 301 | YES |  |  |  | YES | 
US 302 | NO |  |  |  |  | 
US 303 | YES |  | YES |  |  | 
US 304 | YES |  |  |  | YES | 
US 305 | NO |  |  |  |  | 
US 306 | YES |  |  |  | YES | 
US 307 | YES |  |  |  | YES | 
US 308 | YES |  |  |  | YES | 
US 309 | NO |  |  |  |  | 
US 310 | YES |  | YES |  |  | 
… |  |  |  |  |  | 

## Slide 4: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
US 311 (OPTIONAL) | NO |  |  |  |  | 
US 312 | YES |  |  |  | YES | 
US 313 | YES |  |  |  | YES | 
US 314 | YES |  |  |  | YES | 
US 315 | YES |  |  |  | YES | 
US 316 | YES |  |  |  | YES | 
US 317 |  |  |  |  |  | 
US 318 |  |  |  |  |  | 
US 319 |  |  |  |  |  | 
US 320 |  |  |  |  |  | 

## Slide 5: Sprint Execution
Issues | Sprint Backlog (a) | Added issues during sprint (b) | Closed issues from initial planning (c) | Closed issues from added ones (d) | Issues not closed (e) | % Execution | 
 |  |  |  |  |  | Planned (c/a) | Total (c+d)/(a+b)
Number of stories (I) | 16 | 3 | 10 | 3 | 6 | 62.5 | 68
Number of bugs (II) | 0 | 5 | 0 | 5 | 0 | - | 100
Number of tasks (III) | 51 | 3 | 31 | 3 | 6 | 61 | 63
TOTAL |  |  |  |  |  |  | 
Total Estimate | 102 h | 3 | 90 | 3 | 0 | 88 | 88.5

## Slide 6: Work by team member
Chart: Hours / n. tasks
| Diogo Dias - 1161605 | Duarte Dias - 1190539
Horas / tarefas | 2.5 | 2

## Slide 7: Work by type
Chart: Componente
| ESINF | ARQC | BDAD | FSIAP | LAPR3
Componente | 3 | 4 | 9 | 0 | 3

## Slide 8: Sprint 3 - Burndown Chart
Print do JIRA após fecho da sprint
Chart: Sprint 3 - BurnDown
| 44539 | 44545 | 44547 | 44552 | 44564
Line | 86 | 79 | 72 | 67 | 55

## Slide 9: Sprint Review
Date: 4Jan2022
Main conclusions:
We should communicate more
We should give more opinions about the team’s work and each member’s work
We should try to not finish some issues on the last days to the delivery of the project

## Slide 10: Sprint Retrospective
Date: 4Jan2022
What went well?
Most of the US’s were done and are functional and totally tested
What went wrong?
On the day before that the sprint would end, one member of the team quit the project and the course, so the all the issues from that member were not done
Some US’s were not completed
What we’ve learned?
We should have communicate more with each other to avoid not knowing what a member is doing at that moment

## Slide 11: Sprint Retrospective
Date: 4Jan2022
Action items:
Try timeboxing of 2 minutes per person in the daily meeting until the next sprint retrospective
Find more accurate ways to estimate the issues
Try to avoid unnecessary meetings

## Slide 12: Team performance metrics
Chart: 
| Sprint 1 | Sprint 2 | Sprint 3
Velocidade | 4 | 2.8 | 2
Controle (máximo desvio padrão) | 2.6 | 4.5 | 2.4
Burnup | 1 | 0.61 | 0.3