## Slide 1: Class 2DD Group 031 SPRINT 2
Group members:
Diogo Sá Dias (1161605)
Pedro Nascimento (0000000)
Duarte Dias (0000000)
Lara (0000000)
Nuno Oliveira (0000000)
Luís Carlos (0000000)

## Slide 2: Sprint planning – Sprint 2
SPRINT BACKLOG | 
Number of stories | 10
Number of bugs | 3
Number of tasks | 39
Number of Management Tasks | 3
Number of team members | Planned: 6 Actual: 6
Total planned estimation vs execution | Planned hours: 48 Executed hours: 50
Planned Start Date: 15Nov2021 Real Start Date: 15Nov2021
Planned Finished Date: 03Dec2021 Real Finish Date: 05Dec2021

## Slide 3: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
US 201 | Yes |  |  | Yes | Yes | 
US 202 | Yes |  |  | Yes | Yes | 
US 203 | Yes |  |  | Yes | Yes | 
US 204 | Yes |  |  | Yes | Yes | 
US 205 | No |  |  | No | No | 
US 206 | Yes |  |  | Yes | Yes | 
US 207 | Yes |  |  | Yes | Yes | 
US 208 | Yes |  |  | Yes | Yes | 
US 209 | Yes |  |  | Yes | Yes | 
US 210 | Yes |  |  | Yes | Yes | 

## Slide 4: Sprint Execution
Issues | Sprint Backlog (a) | Added issues during sprint (b) | Closed issues from initial planning (c) | Closed issues from added ones (d) | Issues not closed (e) | % Execution | 
 |  |  |  |  |  | Planned (c/a) | Total (c+d)/(a+b)
Number of stories (I) | 10 | 3 | 10 | 3 | 0 | 100 | 100
Number of bugs (II) | 0 | 1 | 0 | 1 | 0 | - | 100
Number of tasks (III) | 39 | 3 | 39 | 3 | 5 | 100 | 100
TOTAL |  |  |  |  |  |  | 
Total Estimate | 46 h | 3 | 46 | 3 | 0 | 100 | 100

## Slide 5: Work by team member
Chart: Hours / n. tasks
| Diogo Dias - 1161605 | Aluno 2 | Aluno 3 | Aluno 4
Horas / tarefas | 2 | 2.5 | 3.5 | 4.5

## Slide 6: Work by type
Chart: Componente
| ESINF | ARQC | BDAD | FSIAP | LAPR3
Componente | 40 | 0 | 40 | 0 | 30

## Slide 7: Sprint Burndown Chart
Print do JIRA após fecho da sprint
Chart: Sprint BurnDown
| dia 1 | dia 5 | dia 10 | dia 15
Line | 36 | 32 | 22 | 0

## Slide 8: Sprint Review
Date:
Main conclusions:
Xxx
Yyy
Zzz

## Slide 9: Sprint Retrospective
Date: 6Dec2021
What went well?
What went wrong?
What we’ve learned?

## Slide 10: Sprint Retrospective
Date:
Action items:

## Slide 11: Team performance metrics
Chart: 
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Métrica 1 | 4.3 | 2.5 | 3.5 | 4.5
Métrica 2 | 2.4 | 4.4 | 1.8 | 2.8
Métrica 3 | 2 | 2 | 3 | 5